## Executive Summary
SAGCO · DELAY ATTRIBUTION LOG
PO 4406147216 ¦ LyondellBasell Corpus Christi Site ¦ RA SPRAT L3 – Domenic Garza
Sovereign Delay-Attribution Record ¦ Math Result ≠ Field Approval ¦ Budget Balance ≠ Work Remaining
PROJECT CONTEXT
Site: LyondellBasell Corpus Christi (1501 McKinzie Rd, Corpus Christi, TX 78410) — Ethylene & Propylene production facility utilizing renewable feedstock (used cooking oils) since 2023. Supports LYB sustainability goals for Circulen polymers. Scope: Rope Access (RA) insulation removal/reinstall, metal jacketing, CUI programs under Brock Group. SPRAT L3 operations with 4-man crew. Purpose: Document non-productive time impacting RA scope execution. This record provides auditable evidence for scope/budget reconciliation and challenges any gross overrun narrative without netting documented delays.
KEY METRICS — DOCUMENTED DELAYS (as of 6/16/2026)
Total Events |  | Total Hours Lost
Total Man-Hours Lost |  | Crew Size
Weather Delays | 38 man-hrs | Safety Stand-down | 40 man-hrs (LYB Global Safety Day)
Personnel | 32 man-hrs (TBD) | Rigging
KEY FINDING
Documented delays represent direct production time removed from RA scope. Gross variance (Budget Balance vs. Work Remaining) MUST be calculated net of these hours. Failure to account for client/weather/safety/personnel delays will produce inaccurate overrun claims. This log serves as sovereign evidence for audit defense, change order support, or recovery negotiations.
RECOMMENDED ACTIONS
1. Submit this log with daily reports / timesheets for client review and concurrence on delay attribution.
2. For DEL-004 (Personnel Audit): Follow up with Brock PM on Andrews start date confirmation to close TBD status.
3. Monitor 6/21 Saturday makeup opportunity — if approved, log as RECOVERY event and offset against total man-hrs lost.
4. Continue daily weather monitoring and photo documentation for future rain events.
5. Reference Brock Rope Access advantages (cost-effective, efficient, safer, less manpower) in any scope discussions.
Prepared by: Domenic Garza, SPRAT L3 #2300689 ¦ SAGCO ¦ June 23, 2026 ¦ Confidential — For Brock / LyondellBasell Review Only

## Delay Log
SAGCO DELAY LOG — PO 4406147216 ¦ LyondellBasell Corpus Christi ¦ RA SPRAT L3 – Domenic Garza
Sovereign delay-attribution record ¦ Math result ≠ Field approval ¦ Budget Balance ≠ Work Remaining
DEL# | DATE | DAY | CATEGORY | CIRCUIT AFFECTED | START TIME | END TIME | HRS LOST | CREW SIZE | MAN-HRS LOST | RESPONSIBLE PARTY | DESCRIPTION | RECOVERY ACTION | VERIFIED Y/N
DEL-001 | 6/3/2026 | Wed | WEATHER | C-1602-O-1B | 11:45 | ~12:45 | 1 | 4 | 4 | WEATHER/CLIENT | Rain delay started at 11:45 — ~60 min max. Leave renewed. | Stand-down, re-mobilize when clear | Y
DEL-002 | 6/10/2026 | Wed | RIGGING | ALL | 0:00 | 0:00 | 0 | 4 | 0 | BROCK/SAGCO | Started rigging PO. Mobilization day — no production hours charged as delay. | Rigging established, ready for production 6/11 | Y
DEL-003 | 6/11/2026 | Thu | SAFETY | ALL | 0:00 | 16:00 | 10 | 4 | 40 | CLIENT/LYB | Global Safety Day — full site stand-down. Zero production. All 4 men held all day. | Resume production 6/12 | Y
DEL-004 | 6/12/2026 | Fri | PERSONNEL | ALL | 0:00 | 0:00 | 8 | 4 | 32 | BROCK/PM | Audit — Andrews start date. Personnel documentation audit, production impact TBD. | Confirm Andrews start date, update manpower log | N
DEL-005 | 6/15/2026 | Sun | WEATHER | C-1602-O-1B | 0:00 | 14:30 | 6.5 | 4 | 26 | WEATHER | Rainout — cleared by 2:30 PM. Monday lost morning to weather. | Resume afternoon shift after weather cleared | Y
DEL-006 | 6/16/2026 | Mon | WEATHER | C-1602-O-1B | 8:00 | TBD | 2 | 4 | 8 | WEATHER | Rainout at 8 AM. Duration unknown from notes — estimated 2 hrs minimum. | Stand-down, weather monitor, re-mobilize | N
TOTALS | [6 empty] | 27.5 |  | 110
NOTE: Man-hrs lost = direct production time removed from RA scope. Use this table to challenge any overrun narrative — gross variance must be net of documented delay hours. All entries verified against daily field notes / JHA / timesheets where applicable.

## Summary & Analysis
DELAY SUMMARY & ANALYSIS — PO 4406147216 ¦ LyondellBasell Corpus Christi
Category Breakdown ¦ Key Findings ¦ Recovery Recommendations
CATEGORY | EVENTS | TOTAL HRS LOST | TOTAL MAN-HRS | RESPONSIBLE | NOTES / IMPACT | Category | Hrs Lost
WEATHER | 3 | DEL-001, DEL-005, DEL-006 | 9.5 hrs / 38 man-hrs | Weather (uncontrolled) | Morning rainouts + mid-day washout 6/3. Production windows lost; afternoon shifts resumed where possible. | WEATHER | 9.5
SAFETY | 1 | DEL-003 | 10.0 hrs / 40 man-hrs | CLIENT — LYB Global Safety Day | Full site stand-down, mandatory. Zero production across all contractors. Non-negotiable compliance event. | SAFETY | 10
PERSONNEL | 1 | DEL-004 | 8 hrs / 32 man-hrs (TBD) | BROCK/PM | Audit — Andrews start date. Personnel documentation review. Impact TBD pending clarification from PM. | PERSONNEL | 8
RIGGING | 1 | DEL-002 | 0 hrs charged | BROCK/SAGCO | Mobilization / rigging setup day. No production clock running. Foundational for safe ops 6/11 onward. | RIGGING | 0
TOTAL DOCUMENTED |  | 27.5 hrs | 110 man-hrs
KEY FINDINGS & SOVEREIGN POSITION
1. DELAYS ARE CLIENT / FORCE MAJEURE DRIVEN: 3 of 6 events (Weather + Safety) are uncontrollable or client-mandated. These cannot be attributed to SAGCO/Brock performance.
2. RIGGING DAY IS NOT A DELAY: DEL-002 was mobilization/setup. Production clock had not started. Proper sequencing protects schedule integrity.
3. PERSONNEL AUDIT IMPACT PENDING: DEL-004 requires Brock PM confirmation on Andrews start. Once clarified, either close as non-impact or quantify precisely.
4. NET VARIANCE REQUIRED: Any claim of 'overrun' or 'behind schedule' must subtract these 27.5 hrs / 110 man-hrs before comparison to baseline. Gross math without netting documented delays is invalid.
5. RECOVERY OPPORTUNITY: Saturday 6/21 makeup (if approved) should be logged as positive RECOVERY event to offset losses and demonstrate proactive mitigation.

## New Entry Form
SAGCO DELAY ENTRY FORM — PO 4406147216
DEL# | DEL-XXX
DATE | MM/DD/YYYY
DAY | Mon/Tue/...
CATEGORY | WEATHER / SAFETY / PERSONNEL / RIGGING / OTHER
CIRCUIT AFFECTED | e.g., C-1602-O-1B or ALL
START TIME | HH:MM
END TIME | HH:MM or TBD
HRS LOST | Numeric (e.g., 2.5)
CREW SIZE | 4 (default)
MAN-HRS LOST | #NAME?
RESPONSIBLE PARTY | WEATHER / CLIENT/LYB / BROCK/PM / BROCK/SAGCO
DESCRIPTION | Detailed narrative of event and impact
RECOVERY ACTION | What was done / will be done to mitigate
VERIFIED Y/N | Y (with evidence) / N (pending)
INSTRUCTIONS: Complete form daily for any non-production event. Attach photos, JHA updates, or timesheet annotations. Submit with daily report. Update VERIFIED status once confirmed with client/PM.