## DELAY_LOG
SAGCO · DELAY LOG ¦ PO 4406147216 ¦ LyondellBasell Corpus Christi ¦ RA SPRAT L3 – Domenic Garza
Sovereign delay-attribution record ¦ Math result ≠ Field approval ¦ Budget Balance ≠ Work Remaining
DEL# | DATE | DAY | CATEGORY | CIRCUIT AFFECTED | START TIME | END TIME | HRS LOST | CREW SIZE | MAN-HRS LOST | RESPONSIBLE PARTY | DESCRIPTION | RECOVERY ACTION | VERIFIED Y/N
DEL-001 | 6/3/2026 | Wed | WEATHER | C-1602-O-1B | 11:45 | ~12:45 | 1 | 4 | 4 | WEATHER/CLIENT | Rain delay started at 11:45 — ~60 min max. Leave rened (leave renewed). | Stand-down, re-mobilize when clear | Y
DEL-002 | 6/10/2026 | Wed | RIGGING | ALL | 0:00 | 0:00 | 0 | 4 | 0 | BROCK/SAGCO | Started rigging PO. Mobilization day — no production hours charged as delay. | Rigging established, ready for production 6/11 | Y
DEL-003 | 6/11/2026 | Thu | SAFETY | ALL | 0:00 | 16:00 | 10 | 4 | 40 | CLIENT/LYB | Global Safety Day — full site stand-down. Zero production. All 4 men held all day. | Resume production 6/12 | Y
DEL-004 | 6/12/2026 | Fri | PERSONNEL | ALL | 0:00 | 0:00 | 8 | 4 | 32 | BROCK/PM | Audit — Andrews start date. Personnel documentation audit, production impact TBD. | Confirm Andrews start date, update manpower log | N
DEL-005 | 6/15/2026 | Sun | WEATHER | C-1602-O-1B | 0:00 | 14:30 | 6.5 | 4 | 26 | WEATHER | Rainout — cleared by 2:30 PM. Monday lost morning to weather. | Resume afternoon shift after weather cleared | Y
DEL-006 | 6/16/2026 | Mon | WEATHER | C-1602-O-1B | 8:00 | TBD | 2 | 4 | 8 | WEATHER | Rainout at 8 AM. Duration unknown from notes — estimated 2 hrs minimum. | Stand-down, weather monitor, re-mobilize | N
TOTALS | [6 empty] | 27.5 |  | 110
NOTE: Man-hrs lost = direct production time removed from RA scope. Use this table to challenge any overrun narrative — gross variance must be net of documented delay hours.

## SUMMARY
DELAY SUMMARY — PO 4406147216 ¦ LyondellBasell CC
CATEGORY | EVENTS | TOTAL HRS LOST | TOTAL MAN-HRS | RESPONSIBLE | NOTES
WEATHER | 3 | DEL-001, DEL-005, DEL-006 | 9.5 hrs / 38 man-hrs (est) | Weather (uncontrolled) | Morning rainouts + mid-day washout 6/3
SAFETY | 1 | DEL-003 | 10.0 hrs / 40 man-hrs | CLIENT — LYB Global Safety Day | Full site stand-down, mandatory, zero production
PERSONNEL | 1 | DEL-004 | TBD | BROCK/PM | Andrews audit — impact TBD pending clarification
RIGGING | 1 | DEL-002 | Mob day, not charged as delay | BROCK/SAGCO | Rigging setup 6/10, no production clock running
KEY FINDING: Documented delays = non-production time that must be subtracted before any 'overrun' calculation is valid. Budget Balance ≠ Work Remaining.
ACTION ITEM: 'Possible work Saturday' — If Saturday 6/21 approved for makeup, log as RECOVERY event and offset against total man-hrs lost.

## NEW_ENTRY
SAGCO DELAY ENTRY FORM
DEL#
DATE
DAY
CATEGORY
CIRCUIT AFFECTED
START TIME
END TIME
HRS LOST
CREW SIZE
MAN-HRS LOST
RESPONSIBLE PARTY
DESCRIPTION
RECOVERY ACTION
VERIFIED Y/N