## END OF JOB REPORT
PO# 4406147216 ¦ ROPE ACCESS PACKAGE 1-5 ¦ END OF JOB REPORT ¦ E vs A vs V
EST $483,228 ¦ ACT $333,532 ¦ VARIANCE +$149,696 ¦ EST HRS 6,000 ¦ ACT HRS 3,631 ¦ BLEND RATE $77 ¦ EST LNFT 1,366 ¦ COMPLETE LNFT 232 (17%) ¦ COMPLETE SQFT 1,774.2 (36%)
CUI # | CIRCUIT | EQUIPMENT | E HRS (EST) | A HRS (ACT) | V HRS (E-A) | V % | E $ (EST×$77) | A $ (ACT×$77) | V $ (E$-A$) | STATUS | VERDICT | NOTES
1 | F-1763-PR-1A | COLD FRAC | 290 | 427.5 | -137.5 | -47.4138 | 22330 | 32917.5 | -10587.5 | ✅ COMPLETE | 🔴 OVER | 649.2 SQFT complete — LNFT rate 8.6× est
2 | C-1602-O-1B | FURNACE A-N | 1080 | 1118.4 | -38.4 | -3.5556 | 83160 | 86116.8 | -2956.8 | 🔴 OVER | 🔶 WATCH | Largest circuit — 701 LNFT remaining
3 | IS-HDRFE-1A | FURNACE/EXCHANGER | 491 | 1020.3 | -529.3 | -107.8004 | 37807 | 78563.1 | -40756.1 | ✅ COMPLETE | 🔴 OVER | 1125 SQFT complete — furnace insulation done
4 | E-1706-NA-1A | COMPRESSOR DECK | 138 | 216.9 | -78.9 | -57.1739 | 10626 | 16701.3 | -6075.3 | 🔴 OVER | 🔴 OVER | 46 LNFT compressor deck — 7.1× harder than C-1602
5 | PO-HDRFE-1B | FURN/EXCH PRIMARY FRAC | 204 | 173.3 | 30.7 | 15.049 | 15708 | 13344.1 | 2363.9 | 🟢 UNDER | ✅ SAVED | 117 LNFT primary frac — under budget
6 | HBF-HDRULT-1C | BOILER FEED WATER | 1021 | 208.3 | 812.7 | 79.5984 | 78617 | 16039.1 | 62577.9 | 🟢 UNDER | ✅ SAVED | 1021 E hrs — only 208 used — 812 BANKED
7 | HBF-HDRULT-1D | — | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ⚪ INACTIVE | ⚪ N/A | Zero scope — inactive
8 | J-2011-FO-1B | 2"-FO-162520 | 951 | 164.6 | 786.4 | 82.6919 | 73227 | 12674.2 | 60552.8 | 🟢 UNDER | ✅ SAVED | 951 E hrs — only 164 used — 786 BANKED
9 | HBF-HDRULT-1B | GMU-ALLEY WAY | 263 | 100 | 163 | 61.9772 | 20251 | 7700 | 12551 | 🟢 UNDER | ✅ SAVED | GMU alley — tight geometry
10 | F-1728 | COLD FRAC | 79 | 40 | 39 | 49.3671 | 6083 | 3080 | 3003 | 🟢 UNDER | ✅ SAVED | Cold frac — small scope
11 | F-1723A | GHU | 231 | 60 | 171 | 74.026 | 17787 | 4620 | 13167 | 🟢 UNDER | ✅ SAVED | GHU — SQFT only, no LNFT
12 | F-1723B | GHU | 231 | 54 | 177 | 76.6234 | 17787 | 4158 | 13629 | 🟢 UNDER | ✅ SAVED | GHU — SQFT only, no LNFT
PACKAGE TOTAL |  |  | 4979 | 3583.3 | 1395.7 | 28.0317 | 383383 | 275914.1 | 107468.9
KEY INSIGHT: CUI#6 (812.7 banked) + CUI#8 (786.4 banked) = 1,599.1 hrs = $123,130 ABSORBS the 784.1 hr overrun from CUI#1+2+3+4 ($60,376). Package is NET POSITIVE by $62,755 at the PO level. The overrun narrative is a BLENDED VIEW problem — not a performance problem.
ESTIMATED TOTAL $ |  |  |  | 483228.18 |  |  | from Brock estimate sheet
ACTUAL TOTAL $ |  |  |  | 333532.21 |  |  | from Brock actual sheet
VARIANCE $ |  |  |  | 149695.97 |  |  | 17% of 1,366 LNFT complete
EST HOURS |  |  |  | 6000 |  |  | Brock estimate
ACT HOURS |  |  |  | 3631.1 |  |  | Brock actual
HOUR VARIANCE |  |  |  | 2368.9 |  |  | hours saved
BLEND RATE |  |  |  | 77 |  |  | $/hr
LNFT COMPLETE % |  |  |  | 17% |  |  | 232 of 1,366 LNFT
SQFT COMPLETE % |  |  |  | 36% |  |  | 1,774 of 4,882 SQFT