## ERU CIRCUIT ENGINE
SAGCO ERU ENGINE ¦ PO# 4406147216 ¦ ROPE ACCESS PACKAGE 1-5 ¦ Target: Cut 784.1 hrs overrun
ALGORITHM: ERU = E - U ¦ CUT_NEEDED = ERU × BLEND_RATE($77) ¦ HOURS_TO_CUT = TARGET_784.1 × (ERU/TOTAL_ERU) ¦ NEW_U = U + HOURS_CUT ¦ NEW_R = E - NEW_U
CUI # | PO # | CIRCUIT | E ESTIMATED | U USED | R REMAINING | ERU STATUS | BLEND RATE $ | $ AT RISK (overrun×BR) | % OF TOTAL OVERRUN | HOURS TO CUT | $ SAVED IF CUT | NEW U AFTER CUT | NEW R AFTER CUT | Q-POINT (U/E) | VERDICT
1 | 4406147216 | F-1763-PR-1A | 290 | 427.5 | -137.5 | 🔴 CRITICAL OVER | 77 | 10587.5 | 17.536 | 137.5 | 10587.5 | 290 | 0 | 1.4741 | ✂️ CUT NEEDED
2 | 4406147216 | C-1602-O-1B | 1080 | 1118.4 | -38.4 | 🔴 OVER | 77 | 2956.8 | 4.8973 | 38.4 | 2956.8 | 1080 | 0 | 1.0356 | ✂️ CUT NEEDED
3 | 4406147216 | IS-HDRFE-1A | 491 | 1020.3 | -529.3 | 🔴 CRITICAL OVER | 77 | 40756.1 | 67.5041 | 529.3 | 40756.1 | 491 | 0 | 2.078 | ⛔ MAJOR CUT
4 | 4406147216 | E-1706-NA-1A | 138 | 216.9 | -78.9 | 🔴 OVER | 77 | 6075.3 | 10.0625 | 78.9 | 6075.3 | 138 | 0 | 1.5717 | ✂️ CUT NEEDED
5 | 4406147216 | PO-HDRFE-1B | 204 | 173.3 | 30.7 | 🟡 NEAR LIMIT | 77 | — | — | 0 | — | 173.3 | 30.7 | 0.84951 | ✅ ON TRACK
6 | 4406147216 | HBF-HDRULT-1C | 1021 | 208.3 | 812.7 | 🟢 LARGE REMAIN | 77 | — | — | 0 | — | 208.3 | 812.7 | 0.20402 | ✅ BANK HOURS
7 | 4406147216 | HBF-HDRULT-1D | 0 | 0 | 0 | ⚪ INACTIVE | 77 | — | — | 0 | — | 0 | 0 | — | ⚪ INACTIVE
8 | 4406147216 | J-2011-FO-1B | 951 | 164.6 | 786.4 | 🟢 LARGE REMAIN | 77 | — | — | 0 | — | 164.6 | 786.4 | 0.17308 | ✅ BANK HOURS
9 | 4406147216 | HBF-HDRULT-1B | 263 | 100 | 163 | 🟢 UNDER | 77 | — | — | 0 | — | 100 | 163 | 0.38023 | ✅ ON TRACK
10 | 4406147216 | F-1728 | 79 | 40 | 39 | 🟡 NEAR LIMIT | 77 | — | — | 0 | — | 40 | 39 | 0.50633 | ✅ ON TRACK
11 | 4406147216 | F-1723A | 231 | 60 | 171 | 🟢 UNDER | 77 | — | — | 0 | — | 60 | 171 | 0.25974 | ✅ ON TRACK
12 | 4406147216 | F-1723B | 231 | 54 | 177 | 🟢 UNDER | 77 | — | — | 0 | — | 54 | 177 | 0.23377 | ✅ ON TRACK
TOTALS |  |  | 4979 | 3583.3 | 1395.7 | TOTAL OVERRUN: 784.1 hrs |  | 60375.7 |  | 784.1 | 60375.7
ALGORITHM: Total Overrun = 784.1 hrs ¦ Target Cut = 784.1 hrs ¦ Blend Rate = $77.0/hr ¦ Dollar Target = $60,375.70 ¦ Proportional cut per circuit = Circuit_Overrun / 784.1 × 784.1
CUI#6 (HBF-HDRULT-1C) R=812.7 hrs + CUI#8 (J-2011-FO-1B) R=786.4 hrs = 1599.1 hrs banked ¦ $ VALUE = $123,130.70 ¦ These two circuits OFFSET the overrun from CUI#3 IS-HDRFE-1A (-529.3) + others

## ALGORITHM
SAGCO ERU ALGORITHM ¦ Variables · Constants · Formulas · Transistor Correlation
From your notebook: Total R × Blend Rate = $ ¦ ERU: E=138 U=216.9 R=-78.9 ¦ Hours over × BR = dollar amount ¦ CUI#6 + CUI#8 = $ saved
VARIABLE | SYMBOL | VALUE (current) | FORMULA | TRANSISTOR MAP | VERDICT ENGINE | NOTES
Estimated Hours | E | 4979.0 total | Given by PO scope | Vcc — total supply | EXPECTED | What the contract says you have
Used Hours | U | 3583.3 total | Timesheets accumulated | Ic — actual flow | ACTUAL | What's been burned so far
Remaining Hours | R | 1395.7 total | R = E − U | Vce — usable margin | VARIANCE | Positive=banked, Negative=OVER
Blend Rate | BR | $77/hr | Given: billing rate to Brock | β — gain multiplier | BURN RATE | Every hour × $77 = dollar impact
Total Overrun | OVR | 784.1 hrs | Sum of all negative R circuits | Rc — restriction | VARIANCE | CUI1+2+3+4 = 784.1 hrs over
Dollar Overrun | $OVR | $60,375.70 | OVR × BR = 784.1 × $77 | Rc × β | VARIANCE$ | 784.1 × 77 = $60,375.70 at risk
Hours to Cut / circuit | HTC | Proportional | HTC = OVR × (Circuit_R / Total_R) | Ib — base input needed | CUT TARGET | Each circuit gets proportional share
Dollar Saved | $SAV | HTC × $77 | $SAV = HTC × BR | Ic × β | ACTUAL$ | If you cut the hours, this is recovered
Q-Point | Q | U/E ratio | Q = U / E | Q-Point | Q-POINT | Q>1.0 = saturated/over, Q<1.0 = ok
New U after cut | U' | U − HTC | U' = U − HTC | New Ic | NEW ACTUAL | Projected used if hours are cut
New R after cut | R' | E − U' | R' = E − U' | New Vce | NEW MARGIN | Should be ≥0 after cut
CUI#6 banked | B6 | 812.7 hrs | E−U for HBF-HDRULT-1C | Positive Vce | OFFSET | $62,578.90 banked — absorbs overrun
CUI#8 banked | B8 | 786.4 hrs | E−U for J-2011-FO-1B | Positive Vce | OFFSET | $60,552.80 banked — absorbs overrun
Combined bank | B6+B8 | 1599.1 hrs | 812.7 + 786.4 | Total positive Vce | VERDICT | $123,130.70 — MORE than enough to cover $60,375 overrun
▶ ANSWER: You don't need to cut 784.1 hrs from overrun circuits. CUI#6 (812.7) + CUI#8 (786.4) = 1,599.1 banked hrs = $123,130 already offset the $60,375 overrun. The VARIANCE is positive at the package level. The overrun narrative is a BLENDED VIEW problem.