## REVERSE TIME ENGINE
SAGCO REVERSE TIME ENGINE ¦ $ Target → Hours → Days → Calendar Date ¦ PO# 4406147216
REVERSE ALGORITHM: HOURS = $ ÷ BLEND_RATE ¦ DAYS = HOURS ÷ (MEN × 10) ¦ LNFT_RATE = LNFT ÷ TOTAL_HRS ¦ DIFFICULTY = C1602_RATE ÷ CIRCUIT_RATE ¦ FINISH_DATE = START + DAYS
CIRCUIT | EQUIPMENT | LNFT | LNFT/DAY (rate) | DIFFICULTY vs C1602 | MEN | $ TARGET (input) | HRS FROM $ | 10HR DAYS | CALENDAR DAYS | START DATE | FINISH DATE | LNFT/HR actual | VERDICT
C-1602-O-1B | FURNACE A-N | 785 | 46.7 | 1.0× | 4 | 74067.13 | 961.9108 | 24.0478 | 16.8094 | 2026-06-17 | 2026-07-03 19:26 | 1.167 | 🟢 BASELINE
F-1763-PR-1A | COLD FRAC | 75 | 46.7 | 1.0× | 4 | 0 | — | — | 1.606 | 2026-06-17 | 2026-06-18 14:33 | 1.168 | ✅ COMPLETE
E-1706-NA-1A | COMPRESSOR DECK | 46 | 6.6 | 7.08× | 4 | 4340.24 | 56.3668 | 1.4092 | 6.9697 | 2026-06-17 | 2026-06-23 23:16 | 0.165 | ⛔ HIGH DIFFICULTY
IS-HDRFE-1A | FURNACE/EXCHANGER | 317 | 46.7 | 1.0× | 4 | 0 | — | — | 6.788 | 2026-06-17 | 2026-06-23 18:55 | 1.167 | ✅ COMPLETE
PO-HDRFE-1B | FURNACE/EXCHANGER PRIM | 117 | 11.7 | 3.99× | 4 | 11039.3 | 143.3675 | 3.5842 | 10 | 2026-06-17 | 2026-06-27 | 0.292 | 🔴 HARD CIRCUIT
HBF-HDRULT-1C | BOILER FEED WATER | 86 | 10.7 | 4.36× | 4 | 8114.36 | 105.3813 | 2.6345 | 8.0374 | 2026-06-17 | 2026-06-25 00:54 | 0.268 | 🔴 HARD CIRCUIT
J-2011-FO-1B | 2"-to-162520 | 126 | 10 | 4.67× | 4 | 11888.48 | 154.3958 | 3.8599 | 12.6 | 2026-06-17 | 2026-06-29 14:24 | 0.25 | 🔴 HARD CIRCUIT
HBF-HDRULT-1B | GMU-ALLEY WKY | 84 | 7.2 | 6.49× | 4 | 7925.65 | 102.9305 | 2.5733 | 11.6667 | 2026-06-17 | 2026-06-28 16:00 | 0.18 | ⛔ HIGH DIFFICULTY
F-1723A | GMU2 | — | 46.7 | 1.0× | 4 | — | — | — | — | 2026-06-17 | — | — | 🟢 BASELINE
F-1723B | GMU2 | — | 46.7 | 1.0× | 4 | — | — | — | — | 2026-06-17 | — | — | 🟢 BASELINE
F-1728 | COLD FRAC | 32 | 46.7 | 1.0× | 4 | 3019.3 | 39.2117 | 0.98029 | 0.68522 | 2026-06-17 | 2026-06-17 16:27 | 1.168 | 🟢 BASELINE
▶ REVERSE KEY: $123,130.70 ÷ $77 = 1,599.1 hrs ¦ 1,599.1 ÷ (4 men × 10) = 39.97 ten-hour days ¦ C-1602 at 46.7 LNFT/day → 39.97 days = 1,867 LNFT completable ¦ E-1706 at 6.6 LNFT/day → 39.97 days = only 264 LNFT ¦ SAME DOLLAR, 7.1× LESS PHYSICAL OUTPUT — that IS the bias proof
DIFFICULTY TABLE: C-1602 RATE vs EACH CIRCUIT
C-1602-O-1B | 46.7 | 1.0× | BASELINE — estimator reference
PO-HDRFE-1B | 11.7 | 4.0× | Primary frac — 4× harder than estimate baseline
HBF-HDRULT-1C | 10.7 | 4.4× | Boiler feed water — tight geometry
J-2011-FO-1B | 10 | 4.7× | 2" pipe cluster — fitting density high
HBF-HDRULT-1B | 7.2 | 6.5× | GMU alley — confined space multiplier
E-1706-NA-1A | 6.6 | 7.1× | Compressor deck — highest difficulty on PO
Formulas:
FINISH DATE = IFERROR(DATEVALUE([START DATE])+[CALENDAR DAYS],"—")